## 1. Product Overview
Item | Description
Product Name | MedVoice-AI
Product Vision/ Purpose | To enable patients to communicate symptoms in their native language and assist doctors with real-time translation, AI-based symptom analysis, and digital OPD records.
Business Goals / Key Success factors | Reduce language barriers, improve consultation speed, increase diagnosis support accuracy, and digitize patient records for hospitals/clinics.
Primary Stakeholders | Patients, Doctors, Hospital Admin, Development Team, Testing Team

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | Patient Registration | US1 | As a patient, I want to register with name, age, and preferred language so that I can use the OPD system. | Registration form, validation, DB storage | Must Have | 5 | To Do | Dev Team | Verify registration flow | QA Team
E2 | Voice Input & Speech-to-Text | US2 | As a patient, I want to describe symptoms by voice in my language so that I can avoid typing. | Mic access, Whisper API integration | Must Have | 8 | To Do | AI Team | Test voice input and transcription | QA Team
E3 | Language Translation | US3 | As a doctor, I want symptoms translated to English so that I can understand patients from any region. | Translation API / multilingual NLP | Must Have | 8 | To Do | AI Team | Check translation accuracy | QA Team
E4 | Symptom Analysis | US4 | As a doctor, I want AI to suggest possible illnesses based on symptoms. | NLP model, symptom dataset | Should Have | 13 | To Do | ML Team | Validate disease prediction | QA Team
E5 | Doctor Dashboard | US5 | As a doctor, I want to view patient history and translated symptoms. | Dashboard UI, history retrieval | Must Have | 8 | To Do | Frontend Team | UI and data flow test | QA Team
E6 | Prescription & Records | US6 | As a doctor, I want to save prescriptions digitally. | Prescription form, DB save/export | Should Have | 5 | To Do | Backend Team | Record save/retrieve test | QA Team
US2
US7
E2 | Dashboard | US5 | As a user, I want to view analytics on a dashboard so that I can see trends quickly. |  | Should Have | 13 | In Progress | Frontend Dev
|  | US6 |  |  | Could Have
US3
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.

## 3. Roadmap
Release |  | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2026-04-03 | Patient Registration, Login, Language Selection | None | Planned
v0.2 | 2026-04-10 | Speech-to-Text + Voice Input | Whisper API | Planned
v0.3 | 2026-04-17 | Translation Module | NLP/Translation API | Planned
v0.4 | 2026-04-24 | AI Symptom Analysis | Dataset + ML model | Planned
v0.5 | 2026-05-01 | Doctor Dashboard + Records | Backend APIs | Planned
v1.0 | 2026-05-08 | Full Demo & Testing | All modules | On Track

## 4. Retrospective
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Good project idea with real healthcare use case | Dataset collection may be difficult | Use sample symptom datasets and demo data | Project Lead
Team coordination and module split | Translation accuracy may vary | Add manual doctor correction option | AI Team